## CoverPage
Flatform | Status
API | PENDING
MOBILE | DOING
PORTAL | DONE
FAILED

## Features
| Tasklist |  |  | Assign |  |  | Work log |  | Description
| Flatform | Module | Status | Assignee | EST Hours | End Date | % | Hours
A |  | PHASE: QUẢN LÝ NGƯỜI DÙNG
I |  | Module: Authentication
1 | API | Get Token | DONE | Tung | 0 | 2019-08-20 | 100% | 3
2 | API | Refresh Token | DONE | Tung | 0 | 2019-08-20 | 100% | 2
3 | API | Get Profile | DONE | Tung | 0 | 2019-08-25 | 100% | 2
4 | API | Logout | DONE | Tung | 1 | 2019-08-26 | 100% | 1
5 | API | Stored token in Database | DOING | Tung | 0 |  | 0%
6 | API | Handle Logs to Database | PENDING | Hao | 0 |  | 0%
7 | API | Middleware check role and permission | PENDING | Hao | 0 |  | 0%
8 | API | Service upload image | DOING | Hao | 0 |  | 0%
9 | API | Integrate Swagger | PENDING | Hao | 0 |  | 0% | 5
10 | PORTAL | Login | DONE | Khanh | 0 |  | 100% | 2
11 | PORTAL | Logout | DONE | Khanh | 0 |  | 100% | 2
12 | PORTAL | Profile | DONE | Khanh | 0 |  | 100% | 2
[5 empty] | 0 |  | 0% | 0
II |  | Module: User
1 | API | List | DONE | Hao | 0 |  | 100% | 1
2 | API | Create | DONE | Hao | 0 |  | 100% | 1
3 | API | Detail | DONE | Hao | 0 |  | 100% | 0.5
4 | API | Update | DONE | Hao | 0 |  | 100% | 1
5 | API | Delete | DONE | Hao | 0 |  | 100% | 0.5
6 | API | Change password | DONE | Hao | 0 |  | 100% | 0.5
7 | PORTAL | List | PENDING | Khanh | 0 |  | 80% | 0 | Remake pending
8 | PORTAL | Create | DOING | Khanh | 0 |  | 90% | 7 | #04/03/1
| PORTAL | +++ Change specs, init user trc (API user/create) để lấy user_id, user_name | DONE | Khanh |  |  | 100% | 1 | #1
9 | PORTAL | Detail | DOING | Khanh | 0 |  | 80% | 1 | #1
10 | PORTAL | Update | DOING | Khanh | 0 |  | 80% | 2 | #2
11 | PORTAL | Delete | DONE | Khanh | 0 |  | 100% | 1 | #1
12 | PORTAL | Change password | DONE | Khanh | 0 |  | 100% | 0.5 | #0.5
[5 empty] | 0 |  | 0% | 0
III |  | Module: User Group
1 | API | List | DONE | Hao | 0 |  | 100% | 1
2 | API | Create | DONE | Hao | 0 |  | 100% | 1
3 | API | Detail | DONE | Hao | 0 |  | 100% | 0.5
4 | API | Update | DONE | Hao | 0 |  | 100% | 1
5 | API | Delete | DONE | Hao | 0 |  | 100% | 0.5
6 | API | Update Status | DONE | Hao | 0 |  | 100% | 0.5
7 | PORTAL | List | PENDING | Phap | 0 |  | 0% | 0
8 | PORTAL | Create | PENDING | Phap | 0 |  | 0% | 0
9 | PORTAL | Detail | PENDING | Phap | 0 |  | 0% | 0
10 | PORTAL | Update | PENDING | Phap | 0 |  | 0% | 0
11 | PORTAL | Delete | PENDING | Phap | 0 |  | 0% | 0
12 | PORTAL | Update Status | PENDING | Phap | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
IV |  | Module: Function Group
1 | API | List | DONE | Tung | 0 | 2019-09-01 | 100% | 1
2 | API | Create | DONE | Tung | 0 | 2019-09-01 | 100% | 2019-05-01
3 | API | Detail | DONE | Tung | 0 | 2019-09-01 | 100% | 1
4 | API | Update | DONE | Tung | 0 | 2019-09-01 | 100% | 1
5 | API | Delete | DONE | Tung | 0 | 2019-09-01 | 100% | 0.5
6 | API | Update Status | DONE | Tung | 0 | 2019-09-01 | 100% | 0.5
7 | API | List Options | DONE | Hao |  |  | 100%
8 | PORTAL | List | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
9 | PORTAL | Create | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
10 | PORTAL | Detail | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
11 | PORTAL | Update | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
12 | PORTAL | Delete | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
13 | PORTAL | Update Status | PENDING | Khanh | 0 |  | 0% | 0 | Implement sau remake list
[5 empty] | 0 |  | 0% | 0
V |  | Module: Function
1 | API | List | DONE | Hao | 0 |  | 100% | 0.5
2 | API | Create | DONE | Hao | 0 |  | 100% | 0.5
3 | API | Detail | DONE | Hao | 0 |  | 100% | 0.5
4 | API | Update | DONE | Hao | 0 |  | 100% | 0.5
5 | API | Delete | DONE | Hao | 0 |  | 100% | 0.5
6 | API | Update Status | DONE | Hao |  |  | 100% | 0.5
7 | PORTAL | List | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
8 | PORTAL | Create | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
9 | PORTAL | Detail | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
10 | PORTAL | Update | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
11 | PORTAL | Delete | DONE | Khanh | 0 | 2019-09-03 | 100% | 0.5
12 | PORTAL | Update Status | PENDING | Khanh | 0 |  | 0% | 0 | Implement sau remake list
[5 empty] | 0 |  | 0% | 0
VI |  | Module: Menu
1 | API | List | DONE | Hao | 0 |  | 100% | 1
2 | API | Create | DONE | Hao | 0 |  | 100% | 1
3 | API | Detail | DONE | Hao | 0 |  | 100% | 0.5
4 | API | Update | DONE | Hao | 0 |  | 100% | 1
5 | API | Delete | DONE | Hao | 0 |  | 100% | 0.5
6 | API | Update Status | DONE | Hao |  |  | 100% | 0.5
7 | PORTAL | List | PENDING | Khanh | 0 |  | 0% | 0
8 | PORTAL | Create | PENDING | Khanh | 0 |  | 0% | 0
9 | PORTAL | Detail | PENDING | Khanh | 0 |  | 0% | 0
10 | PORTAL | Update | PENDING | Khanh | 0 |  | 0% | 0
11 | PORTAL | Delete | PENDING | Khanh | 0 |  | 0% | 0
12 | PORTAL | Update Status | PENDING | Khanh | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
VII |  | Module: City
1 | API | List Options | DONE | Hao | 0 |  | 100% | 0.5
VIII |  | Module: Country
1 | API | List Options | DONE | Hao | 0 |  | 100% | 0.5
IX |  | Module: Province
1 | API | List Options | DONE | Hao | 0 |  | 100% | 0.5
X |  | Module: District
1 | API | List Options | DONE | Hao | 0 |  | 100% | 0.5
XI |  | Module: Ward
1 | API | List Options | DONE | Hao | 0 |  | 100% | 0.5
XII |  | Module: Department
1 | API | List Options | DONE | Hao | 0 |  | 100% | 0.5
XIII |  | Module: Position
1 | API | List Options | DONE | Hao | 0 |  | 100% | 0.5
B |  | PHASE: HỘI VIÊN
I |  | Module: Authentication
1 | MOBILE | Login | PENDING | Thuan | 0 |  | 0% | 0
2 | MOBILE | Logout | PENDING | Thuan | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
II |  | Module: User
1 | MOBILE | Detail | PENDING | Thuan | 0 |  | 0% | 0
2 | MOBILE | Update | PENDING | Thuan | 0 |  | 0% | 0
3 | MOBILE | Create | PENDING | Thuan | 0 |  | 0% | 0
4 | MOBILE | Change password | PENDING | Thuan | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
III |  | Module: Lịch tập
1 |  |  |  |  | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
IV |  | Module: Thông tin hội viên
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
V |  | Module: Đánh giá PT
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
VI |  | Module: Đánh ký tập
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
VII |  | Module: Thông tin PT
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
VIII |  | Module: Thông báo
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
IX |  | Module: Sản phẩm ( không chắc chắn thuộc Pharse B )
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
X |  | Module: Tin tức ( không chắc chắn thuộc Pharse B )
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0
[5 empty] | 0 |  | 0% | 0

## Stored
STT | TÊN STORED PROCEDURE | INPUT | OUTPUT
1 | SYS_USER__FindByUsername | { "UserName": "string" } | { "USERID": "string", "USERNAME": "string", "FULLNAME": "string", "PASSWORD": "string", "EMAIL": "string", "USERGROUPID": [] }
2 | SYS_USER__GetList | { "Orderby": "string", "OrderDes": "string", "PageSize": "number", "PageIndex": "number" } | { "USERID": "string", "FULLNAME": "string", "EMAIL": "string", "PHONENUMBER": "string", "ADDRESS": "string", "GENDER": "bit", "DEFAULTPICTUREURL": "string", "USERGROUPID": [] }
3
4
5
6
7
8
9
10

## BUGS
NO | Flatform | Page | Description | Status | Assignee | DEV note | EST Hours | Due Date
1 | Portal |  | Bỏ menu thêm mới | PENDING | KhanhDTP
6 | Portal |  | Load menu động | PENDING | KhanhDTP
2 | Portal | All page User | - Màn hình danh sách: click vào dòng để vào chi tiết - Thêm actions (edit, xóa, xem chi tiết) mỗi cuối table | DONE | Thuan
3 | Portal | UserGroup | Bỏ is system ở màn hình danh sách | DONE | Thuan
4 | Portal | UserGroup | Label is active đổi thành kích hoạt | DONE | Thuan
5 | Portal |  | Upload avatar thêm process bar or loading | PENDING | KhanhDTP | Avatar (user image) đc encode base64 ở client, và gửi lên chung formData khi add/edit. Nên không cần show loading.
|  |  | Upload avatar giới hạn 4mb | DONE | KhanhDTP
7 | Portal |  | User List: Bỏ ID, tên đăng nhập đổi thành mã nhân viên update theo danh sách column aVy đã gửi | DONE
8 | Portal |  | Validate: thống nhất dùng Form validate của CoreUI | PENDING | KhanhDTP | well noted
9 | Portal | Login | Update lại trang đăng nhập ( bỏ những thông tin chưa cần thiết | DONE | Thuan
10 | Portal | List (All page) | Thêm phần filter | DOING | Thuan
11 |  |  |  | PENDING
12 |  |  |  | PENDING
13 |  |  |  | PENDING
14 |  |  |  | PENDING
15 |  |  |  | PENDING
16 |  |  |  | PENDING
17 |  |  |  | PENDING
18 |  |  |  | PENDING
19 |  |  |  | PENDING
20 |  |  |  | PENDING
21 |  |  |  | PENDING
22 |  |  |  | PENDING
23 |  |  |  | PENDING
24 |  |  |  | PENDING
25 |  |  |  | PENDING
26 |  |  |  | PENDING
27 |  |  |  | PENDING
28 |  |  |  | PENDING
29 |  |  |  | PENDING